## Change Mgmt Plan
PMO360 SOLUTIONS ¦ CHANGE MANAGEMENT PLAN — ADKAR FRAMEWORK
PMO360 Solutions · pmo360.ca
ADKAR Element | Audience | Activity / Intervention | Owner | Start Date | End Date | Status
Awareness | All Staff | Project announcement email from Executive Sponsor | Change Manager |  |  | Planned
Awareness | All Staff | Town hall / info session introducing the project | Change Manager |  |  | Planned
Awareness | Managers | Briefing pack for managers to cascade to teams | Change Manager |  |  | Planned
Desire | Business Leads | 1:1 sessions to address concerns and build buy-in | Change Manager |  |  | Planned
Desire | All Staff | FAQ document; feedback channel established | Change Manager |  |  | Planned
Knowledge | End Users | Role-based training program (classroom or e-learning) | Training Lead |  |  | Planned
Knowledge | Super Users | Super user network training — advanced sessions | Training Lead |  |  | Planned
Knowledge | Managers | Manager toolkit — how to support their teams | Change Manager |  |  | Planned
Ability | End Users | Hands-on practice in UAT / sandbox environment | Training Lead |  |  | Planned
Ability | Super Users | Super user go-live support deployment | Change Manager |  |  | Planned
Reinforcement | All Staff | Go-live celebration and acknowledgement communication | Change Manager |  |  | Planned
Reinforcement | End Users | Post-go-live pulse survey (30/60/90 days) | Change Manager |  |  | Planned
Reinforcement | Managers | Manager check-in cadence post go-live | Change Manager |  |  | Planned

## Resistance Tracker
PMO360 SOLUTIONS ¦ RESISTANCE TRACKER
PMO360 Solutions · pmo360.ca
Stakeholder | Concern / Resistance | Root Cause | Severity (H/M/L) | Mitigation Action | Owner | Status