## Risks
PMO360 SOLUTIONS ¦ RAID LOG — RISKS
PMO360 Solutions · pmo360.ca
ID | Priority | Description | Impact | Owner | Mitigation | Status
R-001 | High | Vendor delivery delay | Schedule slippage | PM | Add 2-week buffer | Open
R-002 | Medium | Key resource availability | Resource gap | Sponsor | Cross-train backup | Open

## Assumptions
PMO360 SOLUTIONS ¦ RAID LOG — ASSUMPTIONS
PMO360 Solutions · pmo360.ca
ID | Assumption | Owner | Validation Method | Status
A-001 | Business units will provide SMEs within 2 weeks of project kick-off | PM | Validate at kick-off | Confirmed
A-002 | Existing infrastructure can support new system without hardware upgrades | Tech Lead | Confirm with IT | Pending

## Issues
PMO360 SOLUTIONS ¦ RAID LOG — ISSUES
PMO360 Solutions · pmo360.ca
ID | Severity | Issue Description | Impact | Owner | Resolution Plan | Status | Date Raised
I-001 | High | Contact form not submitting on live domain | Blocking UAT | PM | Fix DNS config | In Progress | 2025-01-10
I-002 | Medium | Stakeholder availability conflicts with testing schedule | Schedule risk | PM | Reschedule UAT | Open | 2025-01-12

## Dependencies
PMO360 SOLUTIONS ¦ RAID LOG — DEPENDENCIES
PMO360 Solutions · pmo360.ca
ID | Type | Dependency | Impact | Owner | Due Date | Status
D-001 | External | API from third-party vendor | System integration | Vendor | 2025-02-01 | On Track
D-002 | Internal | Sign-off from Legal on privacy policy | Launch readiness | Legal | 2025-01-25 | At Risk