## Risk Register
PMO360 SOLUTIONS ¦ RISK REGISTER
PMO360 Solutions · pmo360.ca
Risk ID | Category | Risk Description | Probability (1-5) | Impact (1-5) | Risk Score | Risk Level | Risk Owner | Mitigation Strategy | Contingency Plan | Status | Date Identified | Last Updated
R-001 | Scope | Scope not clearly defined or approved by all stakeholders | 3 | 4 |  | High | Project Manager | Conduct stakeholder alignment sessions; document signed scope statement | Invoke change control process | Open
R-002 | Schedule | Key dependency on third-party vendor delivery | 3 | 5 |  | High | Project Manager | Weekly vendor check-ins; escalation path defined | Add buffer to schedule; identify alternate vendor | Open
R-003 | Budget | Unplanned scope additions increasing cost | 2 | 4 |  | Medium | Sponsor | Enforce change control; track all scope changes | Request budget contingency approval | Open
R-004 | Resources | Key resource unavailable during critical delivery phase | 2 | 5 |  | High | PM / HR | Cross-train team; document knowledge transfer plan | Identify backup resource pool | Open
R-005 | Technical | Integration between systems fails UAT | 2 | 4 |  | Medium | Technical Lead | Early integration testing; vendor alignment on specs | Extend UAT timeline; escalate to vendor | Open
R-006 | Stakeholder | Executive sponsor disengagement | 2 | 5 |  | High | Project Manager | Regular steering committee; executive status updates | Re-engage through escalation path | Open
R-007 | Compliance | Data privacy requirements not met pre-launch | 1 | 5 |  | Medium | PM / Legal | PIPEDA/privacy review built into project plan | Delay launch; engage legal counsel | Open
R-008 | Change Mgmt | Low end-user adoption post go-live | 3 | 4 |  | High | Change Manager | Training plan; comms strategy; super-user network | Post-go-live support; additional training rounds | Open