## Stakeholder Register
PMO360 SOLUTIONS ¦ STAKEHOLDER MAP & ENGAGEMENT REGISTER
PMO360 Solutions · pmo360.ca
Stakeholder Name | Role / Title | Department | Influence (H/M/L) | Interest (H/M/L) | Engagement Level | Attitude | Communication Needs | Engagement Strategy | Frequency | Owner
| Executive Sponsor | Executive | H | H | Leading | Champion | Monthly steering deck; exception reports | Maintain engagement; present wins early | Monthly | PM
| Project Manager | PMO | H | H | Leading | Champion | Full project visibility | Provide all project artefacts | Weekly | —
| Business Lead | Operations | H | H | Supportive | Neutral | Requirements docs; UAT sign-off | Involve in design; co-own acceptance criteria | Weekly | PM
| IT Lead | Technology | M | H | Aware | Neutral | Technical specs; architecture docs | Engage early on integration design | Weekly | PM
| End Users | Operations | L | M | Unaware | Resistant | Training materials; quick-reference guides | Training sessions; super-user network | At go-live | Change Mgr
| Legal / Compliance | Legal | M | M | Informed | Neutral | Privacy review outcomes | Engage on PIPEDA/compliance requirements | As needed | PM
| Finance | Finance | M | L | Informed | Neutral | Budget reports; change requests | Monthly budget updates | Monthly | PM
| Vendor | External | M | H | Leading | Neutral | SOW; meeting notes; escalations | Weekly vendor syncs; formal escalation path | Weekly | PM

## Engagement Guidance
PMO360 SOLUTIONS ¦ STAKEHOLDER ENGAGEMENT GUIDANCE
PMO360 Solutions · pmo360.ca
ENGAGEMENT LEVELS
Level | Description | When to Use | Key Actions
Unaware | Stakeholder has no knowledge of the project | Early in project; newly identified stakeholder | Introduce project; share overview materials
Resistant | Stakeholder is aware but opposed | When change threatens existing processes or roles | Address concerns directly; involve in design
Neutral | Stakeholder is aware but neither supporting nor opposing | Mid-project; low influence stakeholders | Keep informed; engage on relevant workstreams
Supportive | Stakeholder is aware and supportive | Most business stakeholders post-alignment | Maintain engagement; leverage for advocacy
Leading | Stakeholder is actively involved and driving change | Champions, sponsors, core team | Empower; co-own deliverables; recognize contribution